## Team
Initials | First | Last | Email | GitHub Username
MM | Maryam | Al-Mansour | eng.maryam.al.mansour@gmail.com | MaryamAlMansour
JT | Julie | Traweek | julie.traweek.11@cnu.edu | jtraweek
JL | Jiazhen | Liu | jliu40@stevens.edu | kenpuluma
CS | Celeste | Sakhile | csakhile@stevens.edu | CelesteSakhile
|  |  | GitHub Repository: | 555

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2017-09-19 | 32 |  | 0
2017-10-03 | 24 | 8 | 134 | 850 | 9.4588
2017-10-17 | 16 | 8 | 405 | 670 | 24.2687
2017-10-31 | 8 | 8 | 570 | 390 | 25.3846
2017-11-14 | 0 | 9 | 571 | 391 | 0.15345

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | JT | Completed | 75 | 60 | 13 | 90 | 2017-09-26
US02 | Birth before marriage | MM | Completed | 75 | 60 | 20 | 30 | 2017-10-03
US03 | Birth before death | MM | Completed | 75 | 60 | 21 | 500 | 2017-10-03
US04 | Marriage before divorce | JL | Completed | 75 | 60 | 18 | 30 | 2017-09-25
US05 | Marriage before death | JL | Completed | 75 | 60 | 21 | 35 | 2017-09-25
US06 | Divorce before death | JT | Completed | 75 | 60 | 20 | 60 | 2017-10-01
US07 | Less then 150 years old | CS | Completed | 75 | 60 | 8 | 30 | 2017-09-25
US08 | Birth before marriage of parents | CS | Completed | 75 | 60 | 13 | 75 | 2017-09-26
|  |  |  | 600 | 480 | 134 | 850
Review Results
Keep doing:
Cheking on how everyone is doing with their user story and helping each other
Update Excel file once done with coding with the new values
Frequently talking to the partners and one weekly meeting (every Saturday) to check hoe everything is going.
continious integration : one intergation review to be done every Saturday during the group meeting
Avoid:
unstructured code: we're working on making a better structure to the code (introducing encansulation)
not integrating your code
not writing comments
maintaining better documentation and minutes during our meetings

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Birth before death of parents | CS | Completed | 60 | 60 | 59 | 60 | 2017-10-17
US10 | Marriage after 14 | JT | Completed | 50 | 60 | 10 | 60 | 2017-10-17
US11 | No bigamy | JT | Completed | 90 | 60 | 34 | 240 | 2017-10-17
US12 | Parents not too old | CS | Completed | 88 | 90 | 30 | 60 | 2017-10-17
US14 | Multiple births <= 5 | JL | Completed | 50 | 120 | 40 | 60 | 2017-10-17
US15 | Fewer than 15 siblings | JL | Completed | 50 | 60 | 50 | 80 | 2017-10-17
US16 | Male last names | MM | Completed | 50 | 90 | 13 | 60 | 2017-10-17
US22 | Unique IDs | MM | Completed | 50 | 60 | 35 | 50 | 2017-10-17
|  |  |  | 488 | 600 | 271 | 670
Review Results
Keep Doing:
Start implementation early
Follow TDD Test before Developing
Updating the Burndown Chart
Check on how everyone is doing with their user stories, and offer help if needed
Continuous Integration at each commit
Meet every Saturday for sprint review and sprint planning
Avoid:
Underestimating implementation time for new user stories: Dividing big ones to manageable small user stories
Not defining default time for submission
Start Structuring the coding earlier (Thursday)
1200

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time
US18 | Siblings should not marry | JT | Completed | 30 | 90 | 16 | 60
US21 | Correct gender for role | JL | Completed | 90 | 30 | 8 | 60
US13 | Siblings spacing | JL | Completed | 44 | 30 | 19 | 60
US23 | Unique name and birth date | CS | Completed | 30 | 60 | 19 | 45
US24 | Unique families by spouses | CS | Completed | 30 | 60 | 22 | 45
US28 | Order siblings by age | JT | Completed | 30 | 60 | 33 | 60
US30 | List living married | MM | Completed | 30 | 60 | 27 | 30
US29 | List deceased | MM | Completed | 30 | 60 | 21 | 30
|  |  |  | 314 | 450 | 165 | 390
Review Results:
Keep Doing:
Start implementation early
Follow TDD Test before Developing
Updating the Burndown Chart
Continuous Integration at each commit
Meet every Saturday for sprint review and sprint planning
Make sure all pieces for the output ready before deadline.
Make sure all pieces for the output ready before deadline.
Create individual test output files for ease of integration
Avoid:
Communicating late with other team memebers about how the sprint is going.
Not fully understand what your teammates working on.

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time
US31 | List living single | MM | Completed | 75 | 60 | 23 | 10
US38 | List upcoming birthdays | MM | Completed | 75 | 60 | 24 | 30
US39 | List upcoming anniversaries | CS | Completed | 75 | 60
US35 | List recent births | JT | Completed | 75 | 60 | 14 | 10
US36 | List recent deaths | JT | Completed | 75 | 60 | 18 | 20
US34 | List large age differences | JL | Completed | 75 | 60 | 18 | 10
US42 | Reject illegitimate dates | JL | Completed | 75 | 60 | 3 | 5
|  |  |  | 525 | 420 | 100 | 85
Result Review:
Keep Doing:
Continious Integration
Coomunication in case of unknown conflicts
Understanding how unittest works
Updating the burndown charts
Avoid:
Brute Force implemntation