## Team
Initials | First | Last | Email | GitHub Username
MM | Maryam | Al-Mansour | eng.maryam.al.mansour@gmail.com | MaryamAlMansour
JT | Julie | Traweek | julie.traweek.11@cnu.edu | jtraweek
JL | Jiazhen | Liu | jliu40@stevens.edu | kenpuluma
CS | Celeste | Sakhile | csakhile@stevens.edu | CelesteSakhile
|  |  | GitHub Repository: | 555

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
2017-09-19 | 36 |  | 0
2017-10-03 | 30 | 8 | 134 | 850 | 9.4588
2017-10-17 | 17 | 8 | 271 | 850 | 9.6706

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US01 | Dates before current date | JT | Completed | 75 | 60 | 13 | 90 | 2017-09-26
US02 | Birth before marriage | MM | Completed | 75 | 60 | 20 | 30 | 2017-10-03
US03 | Birth before death | MM | Completed | 75 | 60 | 21 | 500 | 2017-10-03
US04 | Marriage before divorce | JL | Completed | 75 | 60 | 18 | 30 | 2017-09-25
US05 | Marriage before death | JL | Completed | 75 | 60 | 21 | 35 | 2017-09-25
US06 | Divorce before death | JT | Completed | 75 | 60 | 20 | 60 | 2017-10-01
US07 | Less then 150 years old | CS | Completed | 75 | 60 | 8 | 30 | 2017-09-25
US08 | Birth before marriage of parents | CS | Completed | 75 | 60 | 13 | 75 | 2017-09-26
|  |  |  | 600 | 480 | 134 | 850
Review Results
Keep doing:
Cheking on how everyone is doing with their user story and helping each other
Update Excel file once done with coding with the new values
Frequently talking to the partners and one weekly meeting (every Saturday) to check hoe everything is going.
continious integration : one intergation review to be done every Saturday during the group meeting
Avoid:
unstructured code: we're working on making a better structure to the code (introducing encansulation)
not integrating your code
not writing comments
maintaining better documentation and minutes during our meetings

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Birth before death of parents | CS | Completed | 60 | 60 | 59 | 60 | 2017-10-17
US10 | Marriage after 14 | JT | Completed | 50 | 60 | 10 | 60 | 2017-10-17
US11 | No bigamy | JT | Completed | 90 | 60 | 34 | 240 | 2017-10-17
US12 | Parents not too old | CS | Completed | 88 | 90 | 30 | 60 | 2017-10-17
US14 | Multiple births <= 5 | JL | Completed | 50 | 120 | 40 | 60 | 2017-10-17
US15 | Fewer than 15 siblings | JL | Completed | 50 | 60 | 50 | 80 | 2017-10-17
US16 | Male last names | MM | Completed | 50 | 90 | 13 | 60 | 2017-10-17
US22 | Unique IDs | MM | Completed | 50 | 60 | 35 | 50 | 2017-10-17
|  |  |  | 488 | 600 | 271 | 670
Review Results
Keep Doing:
Start implementation early
Follow TDD Test before Developing
Updating the Burndown Chart
Check on how everyone is doing with their user stories, and offer help if needed
Continuous Integration at each commit
Meet every Saturday for sprint review and sprint planning
Avoid:
Underestimating implementation time for new user stories: Dividing big ones to manageable small user stories
Not defining default time for submission
Start Structuring the coding earlier (Thursday)
1200

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US17 | No marriages to descendants | JT | Yet to Start | 120 | 60
US18 | Siblings should not marry | JT | Yet to Start | 30 | 30
US19 | First cousins should not marry | MM | Yet to Start | 60 | 80
US20 | Aunts and uncles | MM | Yet to Start | 80 | 60
US21 | Correct gender for role | JL | Yet to Start | 90 | 30
US13 | Siblings spacing | JL | Yet to Start | 44 | 60
US23 | Unique name and birth date | CS | Yet to Start | 30 | 60
US24 | Unique families by spouses | CS | Yet to Start | 30 | 60
|  |  |  | 484 | 440 | 0 | 0

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US25 | Unique first names in families | JT | Yet to Start
US26 | Corresponding entries | JT | Yet to Start
US27 | Include individual ages | MM | Yet to Start
US28 | Order siblings by age | MM | Yet to Start
US29 | List deceased | JL | Yet to Start
US30 | List living married | JL | Yet to Start
US31 | List living single | CS | Yet to Start
US32 | List multiple births | CS | Yet to Start
|  |  |  | 0 | 0 | 0 | 0

## Project Backlog
Story ID | Story Name | Story Description
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file